## 2022
[7 empty] | 18 | 4 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 1
[7 empty] | 18 |  |  | 3 |  | 3 | 3 |  | 1 | 2 | 1 | 2 | 3
| Team | No | Section | Activity Name | PIC ISG | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD(K) | HC | Act CD | Act HC | Status | Calculate | 2021-10-29 | 2021-10-29 | 2021-11-12 | 2021-11-19 | 2021-11-26
| DEV | 1 | PMG | PMG Improvement Auto BF and Follow up | Minh Dao |  | Plan | bar: Apr to Jun
[6 empty] | Dung | Result | [16 empty] | Finished | bar: Apr to Jun
| DEV | 2 | SMT | Tranfer data IoT to SAP | Hien |  | Plan | [14 empty] | 0.8 |  |  |  | no news | SAP support | Testing 1 or 2 days | Test result OK making go-live schedule | bar: May to Jun
[6 empty] | Tuoc | Result | [16 empty] | Finished
| DEV | 3 | SMT/FE | QR Code for PCB of MW | Dao |  | Plan | bar: May to Jul
[6 empty] | Toan | Result | [16 empty] | Finished | bar: Jun to Jul
| DEV | 4 | ACS | E–approve issue material in and out | Dao |  | Plan | [12 empty] | 21.44 |  | 21.44 |  |  |  | Production member test transfer function next week continue accounting feedback next week | test continue next wed can start | testing FA member next week debit note no add invoice adding now(Dec complete) NG parts return to supplier inovoice use procurement | wainting answer | bar: Jul to Dec
[6 empty] | Hoa | Result | Jul: 1; Aug: 1; Oct: issue/transfer |  |  |  |  | Finished
| DEV | 5 | MCS | MCS Free location | Minh |  | Plan | [13 empty] | 2 |  | 2 |  |  | testing & making November finish MCS test OK QC requirement QTY/ receive QTY | continuew | MCS so so finish QC basic OK tesiting together | meeting MCS/QC next week go-live schedule this version complete first | bar: Jul to Dec
[6 empty] | Nguyen | Result | [16 empty] | Finished | bar: Jul to Nov
| DEV | 6 | FA | Verify Parts in FA automation line | New 2 |  | Plan | [21 empty] | closing | closing | bar: May to Jul
[6 empty] | Thuy | Result | [16 empty] | Finished | bar: Jul to Aug
| DEV | 7 | OQC | Link OQC weight check system with Production | Minh |  | Plan | [12 empty] | 1.98 | 2 | [6 empty] | stop | bar: Apr to Mar
[6 empty] | Ha | Result
| DEV | 8 | SMT/MCS/PUS | Communication software: SMT line vs WH to order urgent materials | Dao |  | Plan | [12 empty] | 5 | [7 empty] | stop | bar: Apr to Mar
[6 empty] | Nguyen | Result
| DEV | 9 | FA | New version of Weight Check for checking more serial number for DECT | Dev |  | Plan | [12 empty] | 4.6 | [7 empty] | stop | bar: Apr to Mar
[6 empty] | Phuong | Result
| DEV | 10 | FA | Microwave Printing label | Dev |  | Plan | [12 empty] | 1.205 |  | 1.21 | [5 empty] | developing | testing | bar: Dec to Mar
[6 empty] | Phuong | Result | [16 empty] | Finished
| DEV | 11 | HR | TimeSheet Checksheet Email sending | Dev |  | Plan | [14 empty] | 6.34 |  |  | 6340 | bar: May to Jun
Add | [5 empty] | Hoa | Result | [16 empty] | Finished | bar: May to Jun
| DEV | 12 | FA | Sound Business | Dev | Quyen | [19 empty] | stop | considering | label printing serial outer link to SCM function | label testing QR code 1st version OK UPS system link | bar: Jul to Dec
Add | [5 empty] | Tan | [17 empty] | Finished | bar: Jul to Nov
| DEV | 13 | PUS/QC | Market Stock control | Dev | P.Anh | [15 empty] | 0.4 |  |  | 368 | bar: Jul to Aug
Add | [5 empty] | Chinh | [17 empty] | Finished | bar: Jul to Aug
Add | DEV | 14 | LOG | Tooling control sheet | Hien | Phuong | Plan | [12 empty] | 5.5 |  | 5.5 |  | Doing | bar: Mar
Add | DEV | 15 | PUS | Tool for issue Commercial Invoice return auto | Dao | Giang | Plan | [12 empty] | 0.6 |  | 0.6 |  | Finished | bar: Nov to Dec
Add | DEV | 16 | FA | Sound Business-Microwave label printing | New | Quyen | Plan | [16 empty] | Finished |  | Finished | bar: Jul to Dec
Add | DEV | 17 | FA | DP, Sound Business Prevent Double ID & Serial No | Minh | Quyen | Plan | [16 empty] | Follow PE | bar: Feb to Mar
Add | DEV | 18 | FA | Sound Business Adding Serial Outer Weight Check & Shrink system | Minh | Quyen | Plan | [12 empty] | 3.9 |  |  | 1 | Finished | 19200 | bar: Dec to Jan
Add | DEV | 19 | FA | Sound Business shipping control | Minh | Cuong | Plan | [12 empty] | 3.9 |  | 3.9 |  | Finished | bar: Nov
Add | DEV | 20 | COS | Auto Material Master | Dao | Luyen | Plan | [12 empty] | 16.4 | [5 empty] | Change to FY22 | bar: Jan to Mar
Add | DEV | 21 |  | Projector Serial label control(Control by Product Seri) | [19 empty] | W5.Mar Hien Test |  | Mar - Apr | bar: Mar
[8 empty] | 2 | 7 | 8 | 12 | 9 | 5 | 5 | 7 | 6 | 4 | 4 | 2
[8 empty] | Oct: DEV TOTAL(PLAN) | 64.525 | 4 | 40.19 | 3
[8 empty] | Oct: DEV TOTAL(RESULT) | 0 | 0
I will confirm each activity the status
Plan -> develop -> Test -> Go live
Tooling control sheet
Tool for issue Commercial Invoice return auto
Sound Business-Microwave label printing
DP, Sound Business Prevent Double ID & Serial No
Sound Business Adding Serial Outer Weight Check & Shrink system
Sound Business shipping control
Auto Material Master
Note on P11: Workflow function
Note on Q11: invoice function

## 3.2023
0
0
Team | No | Section | Activity Name | PIC ISD | PIC Section | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD(K) | HC | Hour | 2022-05-27 | 2022-06-03 | 2022-09-23 | 2022-10-14 | 2022-12-05 | 2022-12-12 | 2023-06-01 | 13/01/2023 | 2023-03-02 | 13/02/2023 | 2023-03-03
DEV | 1 | COS/LOG | Tooling Control Sheet | Dao | Hai | Plan | 1 | 1 | 1 | [9 empty] | 5.4 |  |  | 2022-05-27: Testing, Some revise; 2022-06-03: test so so OK format not match-> training
[5 empty] | Binh | Result | 1 | 1 | 1 | [9 empty] | 5.4 | bar: 2022-06-03
DEV | 2 | MCS | FOSS- Print partcard changing | Minh | Nguyen | Plan | 1 | 1 | 1 | [11 empty] | 576 | 2022-05-27: Change from Box by box to model by model; 2022-06-03: testing with PIC
[6 empty] | Result | 1 | 1 | 1 | [9 empty] | 1.2 |  | 1152 | bar: 2022-06-03
DEV | 3 | DP | DP Prevent Double ID, MAC ID | Minh | Thuy | Plan |  | 1 | 1 | 1 | [11 empty] | 2022-05-27: 2 format already fix start develop; 2022-06-03: next week start
[5 empty] | Tan | Result |  |  | 1 | 1 | bar: 2022-05-27 to 2022-06-03
DEV | 4 | All Depts | Debit Note, Creditnote system upgrade | Phong | All | Plan |  |  | 1 | 1 | [10 empty] | 240 | 2022-05-27: VB6 version now; 2022-06-03: Phong san
[6 empty] | Result |  |  | 1 | 1 | [8 empty] | 1.1 |  | 960
DEV | 5 | PJ-FA | Weight Check Projector for India destination | Minh ->Phong | Quyen | Plan | [5 empty] | 1 | 1 | [8 empty] | 2022-05-27: for special destination
[6 empty] | Result |  |  |  |  | 1 | 1
DEV | 6 | HRS | Elearning System V2 Expand | Dao | Hoa | Plan |  |  | 1 | 1 | 1 | [10 empty] | 2022-09-23: next week make new cource and demo to Iwaura san
[6 empty] | Result |  |  |  |  | 1 | 1 | [6 empty] | 29
DEV | 7 | MW-FA | Microwave OCS upgrade PLC to PC | Dao | Nhien | Plan |  |  | 1 | 1 | 1 | [10 empty] | 2022-05-27: PE setup almost finish collecting data program(shipping process already using); 2022-06-03: file format checking |  |  |  | 0.52368
[5 empty] | Son | Result |  |  | 1 | 1 | bar: 2022-05-27 to 2022-06-03
DEV | 8 | PJ-FA | Projector Traceability Optical Unit | Dao | Son | Plan |  |  |  |  | 1 | 1 | 1 | 1 | [7 empty] | 2022-09-23: minimum version 27 Sep; 2022-10-14: 6 process Next week golive; 2022-12-05: trial
[6 empty] | Result | [6 empty] | 1 | 1
DEV | 9 | All Depts | Total Visualize System | Hien Phong | All | Plan |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 2022-09-23: next week explanation; 2022-10-14: preparation new chart business flow making; 2022-12-05: Move to PSDC, together make; 2022-12-12: PSCD make sample 3 page | Kaizen collect data already |  | Visualize finished. Meeting with others dept for next plan | collect more from AGM
[6 empty] | Result | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1
DEV | 10 | FA/QC | Worker Management System Module: Manpower, Quality, Production(MEBD) | Dao Minh Phong | Hai | Plan |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | at first apply MEBD |  | local discussion scope need make clear next week planning | PV provide adding information next week. Enf of month demo(Plan) | Demo manpower, Quality, Prod | Combine function & waiting Prod prepair device for trial |  | Inform to MG & GM about schedule golive | Prod not yet answer plan | Trial on MCW(already) DP setting | Trial on MCW(already) DP setting
[6 empty] | Result | [6 empty] | 1 | 1 | 1 | 1 | 1 |  | 4.72 |  | 130800
DEV | 11 | MCS | Auto transfer to SAP for outside plan | Minh | Nguyen | Plan | [7 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 | 6 | 2022-09-23: Next month start project; 2022-10-14: scope finish in this month; 2022-12-05: Fix scope and inform change plan; 2022-12-12: Doing | Test 1 scheme Doing other type | Doing other type | Doing other type | Doing other type
[6 empty] | Result | [7 empty] | 1 | 1 | 1 | 1 |  |  | 1
DEV | 12 | PMD | PMD Warehouse management Upgrade | Dao | Dung | Plan | [9 empty] | 1 | 1 | 1 | [10 empty] | Meeting & disscus | Programing | Programing | Delay for PIC resign
[6 empty] | Result | [9 empty] | 1 | 1
DEV | 13 | PMD | Printing area FTP configuration | Hien | Hien | Plan | [7 empty] | 1 | 1 | 1 |  |  |  | 0.5 | 144 | DEV/INFRA |  |  | LAN preparation | LAN OK, Wifi under invest | LAN decide, Dung san request Wifi => must decide this week | Confirm Trinh san finished? | Trinh, Viet install FTP | Configuration service and function use OK. | Server and services completed. LAN waitting PMD setting. Plan Feb finished | Completed. Dept want to add more. => denied
[6 empty] | Result | [9 empty] | 1 |  |  | 0.4 |  | 0.288
DEV | 14 | FA | Auto Print Partcard preparation area | Phong | Thuy | Plan | [8 empty] | 1 | 1 | 1 |  | 1.5 |  | 42 | 2022-10-14: Consider cancel. Focus into items: 11, 12, 15 | Move to March | Move to March | Survey | Programming DIP, Test DP, MCW
[6 empty] | Result | [10 empty] | 1 |  | 6 |  | 2.016
DEV | 15 | SCM | Auto Verify customs declaration data | Phong | Linh | Plan | [9 empty] | 1 | 1 | 1 |  | 0.5 | [9 empty] | Change method - Cancel | Change method - Cancel
Result
DEV | 16 | MCS | Auto Input tracking number to SAP for GR: Local, oversea | Minh | Tam | Plan |  |  |  |  | 1 | 1 | [6 empty] | 1.7 |  | 1.5 | 2022-05-27: 1728; 2022-09-23: finish next week go live
[6 empty] | Result | [5 empty] | 1 | [6 empty] | 2.3 |  | 576
DEV | 17 | All Depts | Traceability New Product | Hien Phong |  | Plan | [10 empty] | 1 | 1 |  |  | 2.304 | [9 empty] | Meeting, not yet have cencept | Meeting, not yet have cencept
Result
[7 empty] | 4 | 5 | 11 | 9 | 8 | 9 | 7 | 9 | 8 | 12 | 12 | 6
[13 empty] | DEV TOTAL(PLAN) | [5 empty] | 0 | 0
[13 empty] | DEV TOTAL(RESULT) | [5 empty] | 0 | 0
Note on W6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on X10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on X16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on X22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on X28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hien
Note on D30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider cancel. Focus to 11, 12, 15
Note on D32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Chane to new process, new method, direct input from SAP to ECUS using API. No need verify

## 8.2020
Team | No | Section | Activity Name | PIC | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD | HC | Progress | Report
DEV | 1 | FA | Etally sheet for Oversea Service Part | Dao | Plan | [13 empty] | 1 | Completed | Jul | bar: Jun to Jul
Result | bar: Jun to Jul
DEV | 2 | MCS | MCS kitting situation auto reflect | Dao | Plan | [13 empty] | 1 | Completed | bar: Jul to Aug
[5 empty] | Result | [15 empty] | ? | bar: Jul to Aug
DEV | 3 | FA | Compare Serial outer and inner PBX's | Minh | Plan | [14 empty] | Completed | Jul | bar: Jun to Aug
Result | bar: Jun to Jul
DEV | 4 | FA | Projector Label printing | Dai | Plan | [14 empty] | Completed | bar: Jun to Aug
[5 empty] | Result | [15 empty] | ? | bar: Jun to Aug
DEV | 5 | FA | Projector quality improvement MEBD | Hien | Plan | [14 empty] | Running Make new app, no need MEBD | bar: Jun to Sep
Result | bar: Jun to Aug
DEV | 6 | MCS | Auto transfer kitting data to SAP | Minh | Plan | [13 empty] | 1 | Meeting | bar: Sep to Oct
Result
DEV | 7 | Common | Video making for IT Training course | Dev | Plan | bar: Sep to Nov; Feb to Mar
Result
DEV | 8 | FA | Microwave traceability | Dao | Plan | [14 empty] | Test FA, Weight, PLC waiting | bar: Aug to Jan
Result | bar: Aug
DEV | 9 | PMG | PMG improvement | Dai | Plan | [12 empty] | 13.5 |  | Survey, Flow, DB | bar: Aug to Jan
Result | bar: Aug
DEV | 10 | QC,MCS | Free location | Minh | Plan | [12 empty] | 8.4 | bar: Nov to Mar
Result
DEV | 11 | PE | RFID inventory | Dao | Plan | [12 empty] | 12.59 | bar: Dec to Mar
Result
DEV | 12 | ISG | Inventory PC automatically | Dev | Plan | bar: Jan to Mar
Result
DEV | 13 | Common | Security Gate | Hien | Plan | [14 empty] | PE modify log -> Make app collect log Network config | bar: Jun to Aug; Nov to Jan
Result | bar: Jun to Aug
[6 empty] | Oct: DEV TOTAL(PLAN) | 34.49 | 3
[6 empty] | Oct: DEV TOTAL(RESULT) | 0 | 0
I will confirm each activity the status
Plan -> develop -> Test -> Go live
1

## 3.2020
77.5
| Team | No | Secton | Activity Name | PIC | Plan/ Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | CD | CD(K) Act | HC | 2021-03-05 | 2021-03-12 | 2021-03-19 | 2021-03-26 | 2021-04-02
| DEV | 1 | FA | Etally sheet for Oversea Service Part | Dao | Plan | [15 empty] | Completed | Completed | Completed | Completed | Completed | bar: Jun to Jul
Result | bar: Jun to Jul
| DEV | 2 | MCS | MCS kitting situation auto reflect | Dao | Plan | [13 empty] | 1pax | 1 | Completed | Completed | Completed | Completed | Completed | bar: Jul to Aug
Result | bar: Jul to Aug
| DEV | 3 | FA | Compare Serial outer and inner PBX's | Minh | Plan | [15 empty] | Completed | Completed | Completed | Completed | Completed | bar: Jun to Aug
Result | bar: Jun to Aug
| DEV | 4 | FA | Projector Label printing | Dai | Plan | [15 empty] | Completed | Completed | Completed | Completed | Completed | bar: Jun to Aug
[6 empty] | Result | [20 empty] | Sept | bar: Jun to Aug
| DEV | 5 | FA | Projector quality improvement MEBD | Hien | Plan | [13 empty] | 63 |  | Completed | Completed | Completed | Completed | Completed | bar: Jun to Sep
[6 empty] | Result | [20 empty] | Sept | bar: Jun to Sep
| DEV | 6 | MCS | Auto transfer kitting data to SAP | Minh | Plan | [13 empty] | 2pax | 3 | develop finish start using | just monitoring weekly inventory check by MCS need confirm acutal. Hanh san(MCS) | no issue | closing meeting need monitor & follow-up | working with normal | 313 314 | bar: Sep to Jan
[6 empty] | Result | [20 empty] | 314 remain | bar: Sep to Jan
| DEV | 7 | Common | Video making for IT Training course | Dev | Plan | [15 empty] | Change | cancel | cancel | cancel | cancel | bar: Sep to Nov; Feb to Mar
Result
| DEV | 8 | FA | Microwave traceability | Dao | Plan | [15 empty] | Completed | Completed | Completed | Completed | Completed | bar: Aug to Jan
Result | bar: Aug to Jan
| DEV | 9 | PMG | PMG improvement | Dai | Plan | [12 empty] | 13.5 | 13.5 |  | Testing almost function OK next week discussion next week complete | have to one more consider additional function -> will do production plan print out -stock card, checksheet- PMG request different stock cart, checksheet (Qty differnent) 100g stockcard, checksheet after production 10g recyle 5g dispose (85g use) I would like to make scheudle DEMO by Dai san (mid of Next week) | STEP1 complete not yet start | SAP BGJ now making (in march) | 6 Apr meeting Just some case PMG find issue. Start using | bar: Aug to Feb
Result | bar: Aug to Dec
| DEV | 10 | QC,MCS | Free location | Minh | Plan | [14 empty] | 2 | discussing device | continue discuss next week |  | teramoto will send document phuong anh san | FY21 contiue | bar: Nov to Mar
Result | bar: Nov to Dec
| DEV | 11 | PE | RFID inventory | Dao | Plan | [12 empty] | 12.59 |  |  | Follow and support only. PE is PIC | Follow and support only. PE is PIC | Follow and support only. PE is PIC | Follow and support only. PE is PIC | cancel | bar: Dec to Mar
Result
| DEV | 12 | ISG | Inventory PC automatically | Dev | Plan | [15 empty] | cancel | cancel | cancel | cancel | cancel | bar: Jan to Mar
Result
| DEV | 13 | Common | Security Gate | Hien | Plan | [15 empty] | PE confirmgn how to solve commuicate with equipment shift change 1 time / 1 day automatically -> next week complete | daily monitoring continue (PE fix already) 1 more function considering | Completed |  | Teramoto or Chung san say Hoan san | bar: Jun to Aug; Nov to Jan
Result | bar: Jun to Aug; Nov to Jan
Add | DEV | 14 | SMT | Compare PDM and Mouting Program | Dai | Plan | [13 empty] | 1.038 |  | Completed | Completed | Completed | Completed | Completed | bar: Aug to Sep
[6 empty] | Result | [20 empty] | Sept | bar: Aug to Sep
Add | DEV | 15 | SMT | SCM Trace back | Minh | Plan | [15 empty] | Completed | Completed | Completed | Completed | Completed | bar: Oct
Result | bar: Oct
| DEV | 16 | ACC | Prices sanction | Dao | Plan | [15 empty] | Completed | Completed | Completed | Completed | Completed | bar: Nov to Dec
Result | bar: Nov
| DEV | 17 | FA | Printing Label for Dect | Hien | Plan | [15 empty] | Completed | Completed | Completed | Completed | Completed | bar: Dec to Jan
Add | [5 empty] | Result
| DEV | 18 | FA | Weight check for Dect | Thao | Plan | [15 empty] | Completed | Completed | Completed | Completed | Completed | bar: Dec to Jan
Add | [5 empty] | Result
| DEV | 19 | FA | Printing Label for DP | Minh | Plan | [15 empty] | Completed | Completed | Completed | Completed | Completed | bar: Dec to Jan
Add | [5 empty] | Result
| DEV | 20 | FA | Weight check for DP | Minh | Plan | [15 empty] | Completed | Completed | Completed | Completed | Completed | bar: Dec to Jan
Add | [5 empty] | Result
| DEV | 21 | FE | ECN Valid Date changing | Hien | Plan | [15 empty] | completed -> next week please show teramoto valid date need change by hand -> automatically | next week please show teramoto |  | demo | demo | bar: Feb
Add | [5 empty] | Result
[7 empty] | Oct: DEV TOTAL(PLAN) | 26.09 | 77.538 | 6
[7 empty] | Oct: DEV TOTAL(RESULT) | 0 |  | 0
[22 empty] | 4152 | 519
1.038
I will confirm each activity the status
Plan -> develop -> Test -> Go live
|  |  |  | PSNV - Fact D server | PV Off
Note on E11: Nguyen Van Hien: Program for FCT verify. Make standard design with all process circle Production confirm MEBD quotation 63K
Note on E13: Nguyen Van Hien not yet report
1