## KH tháng
STT | Dự án | PIC | Nội dung | Thời gian | Golive | Ghi chú
1 | Trace DP new Model | Phong | Xác nhận quy trình thực tế với bộ phận, xác nhận format FCT, Develop FA | W3. Jul | W1.Aug
| E-leave | T.Anh

## 4.E-leave
Panasonic system Networks Vietnam Information System Department
E-LEAVE CONTROL | 147 | PIC | Progress | 2024-05-01 |  | 2024-06-01 |  |  |  | 2024-07-01 |  |  |  | 2024-08-01 |  |  |  | 2024-09-01 |  |  |  | 2024-10-01 |  |  |  | 2024-11-01
|  |  |  | W1 | W2 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Meeting
PERIOD 1: PREPARATION - DEMAND SURVEY | 19 | Hiền | 100% | bar: 2024-05-01 W1 to 2024-06-01 W1
Project Establishment & Environment Preparation | 5 |  | 100%
Make the general project plan/ Review and Approve | 7 |  | 100%
Prepare document + Demand survey (based on confirmed scopes) | 7 |  | 100%
PERIOD 2: SYSTEM ANALYSIS AND DESIGN | 95 | Tuấn Anh | 50% | bar: 2024-06-01 W2 to 2024-10-01 W3
E-Leave | 5 |  | 100% | bar: 2024-06-01 W2 to 2024-08-01 W2
Leave control | 26 |  | 100%
Leave register | 26 |  | 100%
Edit leave |  |  | 100%
Leave control |  |  | 100%
Leave approval |  |  | 100%
Shift working |  | Minh | 100%
Shift register |  |  | 100%
Shift update |  |  | 100%
Shift approve |  |  | 100%
Attendance monitor/approved |  | Tuấn Anh | 100%
Monthly timesheet |  |  | 100%
E-Overtime |  | Tuấn Anh | 100% | bar: 2024-08-01 W3 to 2024-09-01 W3
Overtime register |  |  | 100%
Overtime monitor |  |  | 100%
Overtime approval |  |  | 100%
E-Work |  | Minh | 0% | bar: 2024-09-01 W4 to 2024-10-01 W2
Work from home |  |  | 0%
Remote attendance | 26 |  | 0%
Remote Approval | 5 |  | 0%
Dash board |  | Tuấn Anh | 0% | bar: 2024-10-01 W3 to 2024-10-01 W4
Attendance report | 7 |  | 0%
Overtime report |  |  | 0%
PERIOD 3: SYSTEM BUILIDING AND TESTING | 12 | Minh,Tuấn Anh, Phong | 0% | bar: 2024-10-01 W3 to 2024-10-01 W4
Config the system: Document, config, authorization, main function, report | 3 |  | 0%
Prepare testcase and review/update (2 rounds) | 3 |  | 0%
Customization (Enhancements, Forms, Reports) | 9 |  | 0%
Do testing (SIT round) | 3 |  | 0%
UAT round (Process + Authorization + Customized Functions/ Reports) | 3 |  | 0%
PERIOD 4: FINAL PREPARATION | 7 | Minh,Tuấn Anh, Phong | 0% | bar: 2024-11-01 W1
Training end users | 3 |  | 0%
Transfer/Check configuration to Production system | 3 |  | 0%
Data conversion + Sign-off | 1 |  | 0%
PERIOD 5: GOLIVE AND SUPPORT | 14 | Minh,Tuấn Anh, Phong | 0% | bar: 2024-11-01 W1
System Golive | 2 |  | 0%
Support after Golive | 12 |  | 0%
Main: Minh, Phong, T.Anh
PM: Hien
SIT: System Intergration Testing
UAT: User Acceptance Testing
Go-live
Note on A11: NGUYEN TUAN_Anh: Testing
Note on K13: Delay Need compelete Shift working first
Note on A17: NGUYEN TUAN_Anh: Testing

## 5.Trace DP
Panasonic system Networks Vietnam Information System Department
TRACEABILITY FOR DP NEW MODEL: AE, EW | 147 | PIC | Progress | 2024-06-01 |  |  |  | 2024-07-01 |  |  |  | 2024-08-01 |  |  |  | 2024-09-01
|  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Meeting
PERIOD 1: PREPARATION - DEMAND SURVEY | 19 | Hiền | 100% | bar: 2024-06-01 W1 to 2024-06-01 W2
Project Establishment & Environment Preparation | 5 |  | 100%
Make the general project plan/ Review and Approve | 7 |  | 100%
Prepare document + Demand survey (based on confirmed scopes) | 7 |  | 100%
PERIOD 2: SYSTEM ANALYSIS AND DESIGN | 95 | Phong | bar: 2024-06-01 W3 to 2024-07-01 W4
Concept confirmation with department | 5 |  | 100%
Function and database develop | 26 |  | 94%
SMT - PCB laser marking | 26 |  | 100%
DIP | 26 |  | 100%
FCT | 5 |  | 70%
FA | 7 |  | 100%
Weight Check - Packing |  |  | 100%
PERIOD 3: SYSTEM BUILIDING AND TESTING | 12 |  | 82% | bar: 2024-08-01 W1
Config the system: Document, config, authorization, main function, report | 3 |  | 100%
Prepare testcase and review/update (2 rounds) | 3 |  | 100%
Customization (Enhancements, Forms, Reports) | 9 |  | 100%
Do testing (SIT round) | 3 |  | 70%
UAT round (Process + Authorization + Customized Functions/ Reports) | 3 |  | 40%
PERIOD 4: FINAL PREPARATION | 7 |  | 0% | bar: 2024-08-01 W3
Training end users | 3 |  | 0%
Transfer/Check configuration to Production system | 3 |  | 0%
Data conversion + Sign-off | 1 |  | 0%
PERIOD 5: GOLIVE AND SUPPORT | 14 |  | 0% | bar: 2024-08-01 W4
System Golive | 2 |  | 0%
Support after Golive | 12 |  | 0%
Main: Phong
PM: Hien
SIT: System Intergration Testing
UAT: User Acceptance Testing
Go-live
Under study and discuss with department
Note on I14: Testing.
Note on I15: Delay 1/7: PE confirm: 2 format log Format 1: OK Format 2: Request SCBU change => Next Wed inform

## 12.E-chop
Panasonic system Networks Vietnam Information System Department
E-CHOP IQC | 147 | PIC | Progress | 2024-07-01 |  |  |  | 2024-08-01 |  |  |  | 2024-09-01 |  |  |  | 2024-10-01
|  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Meeting
PERIOD 1: PREPARATION - DEMAND SURVEY | 19 | Hiền | 100% | bar: 2024-07-01 W1 to 2024-07-01 W2
Project Establishment & Environment Preparation | 5 |  | 100%
Make the general project plan/ Review and Approve | 7 |  | 100%
Prepare document + Demand survey (based on confirmed scopes) | 7 |  | 100%
PERIOD 2: SYSTEM ANALYSIS AND DESIGN | 95 | Phong | bar: 2024-07-01 W3 to 2024-08-01 W4
Concept confirmation with department | 5 |  | 100%
Function and database develop | 26 |  | 94%
| 26 |  | 100%
| 26 |  | 100%
| 5 |  | 70%
| 7 |  | 100%
100%
PERIOD 3: SYSTEM BUILIDING AND TESTING | 12 |  | 82% | bar: 2024-09-01 W1
Config the system: Document, config, authorization, main function, report | 3 |  | 100%
Prepare testcase and review/update (2 rounds) | 3 |  | 100%
Customization (Enhancements, Forms, Reports) | 9 |  | 100%
Do testing (SIT round) | 3 |  | 70%
UAT round (Process + Authorization + Customized Functions/ Reports) | 3 |  | 40%
PERIOD 4: FINAL PREPARATION | 7 |  | 0% | bar: 2024-09-01 W3
Training end users | 3 |  | 0%
Transfer/Check configuration to Production system | 3 |  | 0%
Data conversion + Sign-off | 1 |  | 0%
PERIOD 5: GOLIVE AND SUPPORT | 14 |  | 0% | bar: 2024-09-01 W4
System Golive | 2 |  | 0%
Support after Golive | 12 |  | 0%
Main: Phong
PM: Hien
SIT: System Intergration Testing
UAT: User Acceptance Testing
Go-live